## Instructions
Vendor Security Evidence & Remediation Management Workbench
Solvane Cloud Technologies (fictional) — Project 3 companion workbook to eramba Community
PURPOSE
This workbook holds the detailed operational data that eramba Community cannot structure natively (custom fields such as Business Owner, Contract Owner, Renewal Date are an Enterprise-only feature in eramba).
eramba holds: supplier records, risk scoring (Likelihood x Impact), and the findings/remediation workflow.
This workbook holds: vendor operational metadata, evidence tracking, control mapping detail, and the working copy of findings/remediation that feeds Power BI.
HOW TO USE EACH TAB
Vendor Inventory — one row per vendor. Fill in Business Owner, Risk Owner, Contract Owner, Renewal Date and Reassessment Date (yellow cells) as you validate each vendor.
Evidence Tracker — one row per required evidence item per vendor, pre-populated from the tier requirements. Update Received Status, Date Received and Expiry/Review Date (yellow cells) as evidence comes in.
Control Mapping — reference table linking evidence types to ISO/IEC 27001:2022 supplier-relationship controls.
Findings Log — the 7 predefined findings from the project specification. Update Date Identified, Inherent Risk, Residual Risk and Status (yellow cells) as you work each finding.
Remediation Tracker — one remediation action per finding that requires one. Update Owner, Target Date, Status, Validation Result and Closure Evidence (yellow cells).
NOTE
All vendors, contacts, findings and evidence in this workbook are FICTIONAL sample data created for portfolio demonstration purposes only.

## Vendor Inventory
Vendor Inventory
One row per vendor — yellow cells are for you to complete
Vendor | Function | Tier | Business Owner | Risk Owner | Contract Owner | Renewal Date | Reassessment Date | Status
AWS | Cloud hosting/infrastructure | Critical | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-03-24 | Active - Remediation In Progress
Stripe | Payment processing | Critical | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-03-25 | Active - Assessed
Salesforce | CRM/customer data | Critical | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-03-25 | Active - Remediation In Progress
Datadog | Monitoring/logging | High | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-06-25 | Active - Assessed
GitHub | Source code repository | High | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-06-25 | Active - Assessed
Brightline Dev Partners | Contract engineering / production access | High | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-01-25 | Active - Remediation In Progress
SendGrid | Transactional email | Medium | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-09-25 | Active - Assessed
Zendesk | Customer support / PII | High | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-01-25 | Active - Remediation In Progress
Gusto | HR/payroll / employee PII | High | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2026-11-25 | Active - Remediation In Progress
DocuSign | E-signature/contracts | Medium | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-09-25 | Active - Assessed
Redshield Security | Annual penetration testing | Medium | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2027-03-25 | Active - Remediation In Progress
Pulsemetric | Web/product analytics | Low | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2028-03-25 | Active - Assessed
Nexus Office Supply | Hardware procurement | Low | Admin Admin | Olawale Akinbola | Admin Admin | 2027-09-25 | 2028-03-25 | Active - Assessed

## Evidence Tracker
Evidence Tracker
One row per required evidence item per vendor, by tier — yellow cells are for you to complete
Vendor | Tier | Required Evidence | Received Status | Date Received | Expiry / Review Date
AWS | Critical | SOC 2 Type II or ISO 27001 certification | Not Received
AWS | Critical | Signed DPA | Not Received
AWS | Critical | Annual penetration-test summary/attestation | Not Received
AWS | Critical | Completed security questionnaire | Not Received
AWS | Critical | Subprocessor list | Not Received
AWS | Critical | Named incident-response contact and SLA | Not Received
Stripe | Critical | SOC 2 Type II or ISO 27001 certification | Not Received
Stripe | Critical | Signed DPA | Not Received
Stripe | Critical | Annual penetration-test summary/attestation | Not Received
Stripe | Critical | Completed security questionnaire | Not Received
Stripe | Critical | Subprocessor list | Not Received
Stripe | Critical | Named incident-response contact and SLA | Not Received
Salesforce | Critical | SOC 2 Type II or ISO 27001 certification | Not Received
Salesforce | Critical | Signed DPA | Not Received
Salesforce | Critical | Annual penetration-test summary/attestation | Not Received
Salesforce | Critical | Completed security questionnaire | Not Received
Salesforce | Critical | Subprocessor list | Not Received
Salesforce | Critical | Named incident-response contact and SLA | Not Received
Datadog | High | Security questionnaire | Not Received
Datadog | High | Certification/vendor attestation | Not Received
Datadog | High | Signed DPA | Not Received
Datadog | High | Incident-notification clause | Not Received
GitHub | High | Security questionnaire | Not Received
GitHub | High | Certification/vendor attestation | Not Received
GitHub | High | Signed DPA | Not Received
GitHub | High | Incident-notification clause | Not Received
Brightline Dev Partners | High | Security questionnaire | Not Received
Brightline Dev Partners | High | Certification/vendor attestation | Not Received
Brightline Dev Partners | High | Signed DPA | Not Received
Brightline Dev Partners | High | Incident-notification clause | Not Received
SendGrid | Medium | Lightweight questionnaire | Not Received
SendGrid | Medium | Standard contract security clause | Not Received
Zendesk | High | Security questionnaire | Not Received
Zendesk | High | Certification/vendor attestation | Not Received
Zendesk | High | Signed DPA | Not Received
Zendesk | High | Incident-notification clause | Not Received
Gusto | High | Security questionnaire | Not Received
Gusto | High | Certification/vendor attestation | Not Received
Gusto | High | Signed DPA | Not Received
Gusto | High | Incident-notification clause | Not Received
DocuSign | Medium | Lightweight questionnaire | Not Received
DocuSign | Medium | Standard contract security clause | Not Received
Redshield Security | Medium | Lightweight questionnaire | Not Received
Redshield Security | Medium | Standard contract security clause | Not Received
Pulsemetric | Low | Standard procurement terms only | Not Received
Nexus Office Supply | Low | Standard procurement terms only | Not Received

## Control Mapping
Control Mapping
Reference: evidence type mapped to ISO/IEC 27001:2022 supplier-relationship controls
Evidence / Activity Type | ISO/IEC 27001:2022 Control | Control Title
SOC 2 Type II / ISO 27001 certification | A.5.20 / A.5.22 | Addressing security within supplier agreements / Monitoring, review, change management
Signed DPA | A.5.20 | Addressing information security within supplier agreements
Penetration-test summary / attestation | A.5.22 | Monitoring, review and change management of supplier services
Security questionnaire | A.5.19 | Information security in supplier relationships
Subprocessor list | A.5.22 | Monitoring, review and change management of supplier services
Incident-response contact and SLA | A.5.21 / A.5.24 | Managing information security in the ICT supply chain / Incident management planning
Incident-notification clause | A.5.21 | Managing information security in the ICT supply chain
Standard contract security clause | A.5.20 | Addressing information security within supplier agreements
Privileged / production access grants | A.8.2 | Privileged access rights
Vendor reassessment cadence | A.5.19 | Information security in supplier relationships

## Findings Log
Findings Log
The 7 predefined findings — yellow cells are for you to complete
Finding ID | Vendor | Description | Severity | Control Gap | Date Identified | Inherent Risk | Residual Risk | Status
F1 | Brightline Dev Partners | Expired SOC 2 | High | A.5.22 | 2026-09-25 | High | Medium | Open
F2 | Zendesk | No signed DPA despite PII processing | High | A.5.20 | 2026-09-25 | High | Medium | Open
F3 | Salesforce | Subprocessor list not reviewed for 18 months | Medium | A.5.22 | 2026-09-25 | Medium | Medium | Open
F4 | Redshield Security | No incident-notification clause in MSA | Medium | A.5.21 | 2026-09-25 | Medium | Medium | Open
F5 | Gusto | Reassessment overdue by 6 months | Medium | A.5.22 | 2026-09-25 | Medium | Medium | Open
F6 | AWS | No internal shared-responsibility review record | Low | A.5.19 | 2026-09-25 | Low | Low | Open
F7 | Nexus Office Supply | Incorrectly classified as Medium; should be Low | Low | Tiering accuracy | 2026-09-25 | Low | Low | Closed - No Action Needed

## Remediation Tracker
Remediation Tracker
One remediation action per finding — yellow cells are for you to complete
Finding ID | Vendor | Remediation Action | Owner | Target Date | Status | Validation Result | Closure Evidence
F1 | Brightline Dev Partners | Request updated SOC 2 report; suspend production access pending receipt; 30-day SLA. | Olawale Akinbola | 2026-10-25 | Open
F2 | Zendesk | Legal executes DPA within 45 days; escalate vendor owner. | Olawale Akinbola | 2026-11-09 | Open
F3 | Salesforce | Request current subprocessor list and establish annual review. | Olawale Akinbola | 2026-11-25 | Open
F4 | Redshield Security | Amend MSA with 24-hour breach-notification requirement. | Olawale Akinbola | 2026-11-25 | Open
F5 | Gusto | Trigger reassessment and realign cadence. | Olawale Akinbola | 2026-10-25 | Open
F6 | AWS | Document the shared-responsibility review. | Olawale Akinbola | 2026-10-10 | Open
F7 | Nexus Office Supply | Reclassify to Low; no further action required. | Olawale Akinbola | 2026-09-25 | No Action Needed | Reclassification confirmed | Tier updated to Low in eramba Third Party record